## Slide 1
P26 PS
POST-MORTEM
From Feature Implementation to Lifecycle Control
Review B → P27/P28 Alcedo–Zion collaboration improvement
Prepared for Clare / Justin | 10/E Zion workshop
Notes: Opening: This is a PS-involved collaboration review, not an MWI-only issue review. The approved thesis is that implementation alone does not complete a customer customization lifecycle.

## Slide 2
Scope and review boundary
A PS-involved collaboration review, with customization as the lead lens
IN SCOPE — P26 PS-INVOLVED
PS customization and feature governance
AP-IMS / MIPC collaboration
Relay Metrics and interface evolution
ECC/OOS, Call Performance, registration
eSIM/SIM and customer-specific debugging
MWI, release, QPR and long-tail support
TWO VIEWS OF THE SAME EVIDENCE
EXTERNAL
Joint Alcedo/Zion interface, shared evidence, joint improvement, Zion feedback and commitments.
INTERNAL
Alcedo-only R&R, coverage, access side effects, handoff, escalation, decision and long-tail planning.
Owner context: Hsuanchang = effective PS Lv1 DRI from 2025; Aoss = historical PS Lv1 context.
Notes: External does not expose private source mechanics or the intentional firewall rationale. Internal may contain detailed Alcedo R&R and operating side effects.

## Slide 3
Established P26 co-working model
Four mechanisms operated across one feature-to-closure lifecycle
1. Feature
Customization sync
Scope / DRI / validation
2. Issue
Coordinator / DRI / RD
MWI / CR / customer update
3. Technical
Workshops / deep dives
Logs / RCA / workaround
4. Project
Time-zone support
Handoff / release / escalation
Intake
→
Scope + owner
→
Technical decision
→
Implementation / fix
→
Validation
→
Release + closure
P26 lesson lens: mechanisms existed; the execution bridge was not always explicit.
Notes: This recap follows the preparation deck requirement. It is not a meeting list; it is the operating model that the events and cases test.

## Slide 4
Good points to retain
P26 established useful mechanisms — with clear limits
Structured feature alignment
Scope, interface, DRI, validation and delivery discussion were connected.
Persistent technical enablement
AP-IMS/MIPC Q&A and deep dives built shared vocabulary.
Living shared reference
Relay Metrics tracked definitions, support type, status and delivery phase.
Execution gates
MWI cadence, priority classes and release gates made urgency visible.
Boundary awareness
Joint development, customer validation and Alcedo validation were distinguished.
Quantified context (with snapshot labels): 1,200+ metric definitions; 218 MWI items / 111 open on 2026/4/21.
Notes: Do not present these as unconditional success claims. Some are conditional strengths: cadence and reference existed, but execution depth and closure still varied.

## Slide 5
P26 collaboration gaps identified
Neutral system-level observations, not team blame
R&R / routing
Coordination, technical ownership, access and decision authority can converge on one path.
Technical coverage
Time-zone relay exists; matching technical peer/RD depth is not always available.
Lifecycle ownership
Implementation, validation, release, QPR and retirement can span different owners.
Cross-module convergence
Customer scenarios cross AP, Modem, SIM, hardware and network boundaries.
Evidence anchors: MWI / US support, eSIM extra-bytes, SIM Lock, Relay Metrics, QPR handoff.
Notes: Use the term collaboration gaps identified on slide. The preparation deck calls for areas for improvement; the neutral title keeps manager-level tone.

## Slide 6
Key events: feature-to-lifecycle control formation
Actual workshops and reviews that changed the collaboration model
2023/12–2024/11
AP-IMS evolution
Interface/API enablement → topic-specific decisions and ongoing Q&A
2024/9/24
PS customization workshop
Feature scope, interface documents, information boundary, DRI and delivery discussion
2024–present
Relay Metrics
Living cross-layer reference; new metrics, support type and delivery phases continue
2024–2025
FLD1/FLD2/Exception
Scope lock, validation categories, technical/commercial boundary, late-request control
Scale indicators: 4-day PS Deep Dive; ~450 metric items in item-level follow-up; 1,200+ living catalogue (not additive).
Notes: Key events are event-anchored and PS-filtered. The 2024/11 workshop had multiple topics; only topic-specific decisions should be attributed to each topic.

## Slide 7
Key events: execution, verification and post-MP long-tail
When features met certification, devices, release gates and field support
MWI / ECC-OOS
High-frequency review, patch, retest and release gates; Call Performance remained less converged.
eSIM extra-bytes
P0 partner-visible issue; 6/8 monitored devices reproduced; environment and circuit readiness gaps surfaced.
SIM Lock
Post-MP/in-market GID1 read-back chain connected AP/Modem/NVRAM/eSIM/IMS and QPR.
QPR / handoff
P26 workarounds, successor fixes, retirement and continuing support must remain linked.
Long-tail = post-MP QPR support + workaround retirement + next-program handoff + continuing product support.
Notes: Security hot-fix is an MWI substream, not a separate post-MP event. SIM Lock counts from different snapshots must be reconciled before external use.

## Slide 8
Lesson 1 — Feature Verification & Enablement Matrix
A feature is not complete when implementation is complete
Mandatory fields before commitment
Feature / carrier-scenario
Default ON/OFF
Ownership
Alcedo UT/RDIT
SV/FO + rationale
Zion device IT
Acceptance criteria
Release / QPR
Closure owner
Internal action
DRI completes matrix; SV/FO reviews “SV not needed” rationale; commitment gate blocks undefined verification.
External joint action
Alcedo + Zion confirm carrier/scenario enablement, joint-development boundary, device IT and acceptance owner.
Notes: This is an editable matrix mockup. It directly captures the user-identified issue: default state, carrier enablement, joint development, Alcedo self-contained validation versus Zion device IT.

## Slide 9
Lessons 2–3 — Two readiness gates before commitment
People/decision coverage and test/evidence readiness are separate gates
Gate A — Coverage ready
Primary + backup
MUS daytime peer
HQ/domain owner
Decision authority
Escalation trigger
→
Gate B — Evidence ready
Device / AP / SIM / network
Logs / simulator / circuit
Scenario + pass criteria
Validation owner
Accepted risk if missing
→
Commitment ready
Feature / issue can enter
implementation, certification
or release commitment.
P26 evidence: US-daytime technical-peer gap; postponed rotation; eSIM environment/device/circuit gaps.
Proposed measure: gate completed or management-accepted risk recorded before commitment.
Notes: Coverage and verification readiness are related but distinct. Do not merge them into one vague readiness statement.

## Slide 10
Internal lessons learned / Alcedo optimization
Preserve governance; separate the operating roles
Keep the intentional partner-account firewall
Separate access coordination from technical ownership
Define primary / backup / coordinator routing
Make MUS triage vs HQ/RD fix ownership explicit
Assign cross-module convergence owner
Maintain seven-year long-tail planning internally
Internal operating model
Coverage & Routing Matrix + Feature Verification Matrix are phase-gated artifacts.
Manager decision boundary
Technical feasibility ≠ delivery commitment. SV/FO decision ≠ customer system acceptance.
Measure
Primary/backup named before execution peak; handoff retains scenario, evidence, next action and release/QPR disposition.
Notes: This slide is Alcedo-internal. Do not present firewall rationale or Hsuanchang bottleneck as a Zion criticism.

## Slide 11
External lessons learned / joint optimization
A shared contract at the Alcedo–Zion interface
Default ON/OFF and carrier/scenario scope
Alcedo self-contained vs joint development
Alcedo validation vs Zion device/system IT
Customer-time technical counterpart + backup
Required device/log/test assets and acceptance criteria
QPR / next-program disposition for living items
Workshop sequence
Shared evidence → Joint improvement → Zion feedback / commitment → Action items
Notes: External content is macro and jointly discussable. It does not expose PKB, Teams, private account policy, or internal source mechanics.

## Slide 12
P27/P28 proposed operating artifacts
Four prioritized artifacts — proposals, not yet implemented capabilities
P1
Feature Verification & Enablement Matrix
Closes enablement / validation ambiguity
Complete before feature commitment
P2
Coverage & Routing Matrix
Closes technical-peer / decision coverage gap
Ready before execution peak
P3
Joint Verification Readiness Gate
Closes late discovery of missing assets
Gate complete or risk accepted
P4
Carry-forward / Long-tail Register
Closes QPR / workaround handoff loss
Owner + retirement status
Proposed adoption measures: completion before commitment; named primary/backup; readiness gate disposition; carry-forward owner/retirement status.
Notes: The four artifacts are the concrete P27/P28 proposal. Measures are proposed adoption measures, not P26 achieved results.

## Slide 13
Zion workshop decisions and action register
What we need to align for P27/P28
Decision / input
Zion choice / feedback
Alcedo owner
Zion owner
Target / dependency
Adopt four-artifact model
Accept / modify
PS Lv1 + PM
Zion PS lead
P27/P28 planning
Feature verification boundary
Confirm device IT scope
Feature DRI / SV
Zion feature DRI
Before commitment
Customer-time counterpart
Nominate primary/backup
MUS / HQ
Zion US TL
Before execution peak
Readiness gate
Agree participation
Alcedo PM / DRI
Zion validation
Before high-risk test
Closing takeaway: retain P26 collaboration forums; add explicit feature-to-lifecycle control in P27/P28.
Open questions and commitments to be completed in the workshop.
Notes: S14 merged into S13 after rehearsal feedback. This is the workshop action slide and close. Capture actual Zion feedback live; the table currently contains proposed decision prompts.