## Slide 1
Re-cap. Established Co-working Model
P26 collaboration used a fixed weekly rhythm, supplemented by on-demand technical discussion
WEDNESDAY — PS WEEKLY SYNC
Fixed weekly forum
PS customization features
• requirement / scope alignment
• feature status and DRI
• interface / validation boundary
• follow-up and delivery tracking
FRIDAY — SIM WEEKLY SYNC
Fixed weekly forum
SIM / eSIM-related customization
• requirement and feature status
• implementation / issue follow-up
• validation and customer dependency
• P26/P27 carry-forward
ON-DEMAND SMALL GROUP
No fixed frequency
Triggered by important issue, technical gap or decision need
May be daily; several sessions may be arranged on the same day
Deep dive, log review, RCA, workaround, test or owner alignment
Operating pattern: 2 fixed weekly forums + demand-driven technical collaboration
Fixed meetings provide continuity; small groups provide depth and faster convergence for specific topics.
Notes: Confirmed cadence: Wednesday PS weekly sync; Friday SIM weekly sync; on-demand small groups have no fixed frequency and may occur daily or multiple times per day.

## Slide 2
Scope and review boundary
Customization is the lead lens; evidence covers the wider PS-involved lifecycle
P26 PS-INVOLVED
PS customization / FLD1 / FLD2 / Exception
AP-IMS / MIPC / registration / voice
Relay Metrics
ECC / OOS / Call Performance
eSIM / SIM / debugging
MWI / release / QPR / handoff
EXTERNAL — JOINT VIEW
Alcedo + Zion interface
Shared evidence
Joint improvement
Customer-time counterpart
Test / validation boundary
Zion feedback / commitment
INTERNAL — ALCEDO VIEW
R&R / routing
MUS / HQ / RD coverage
Access side effects
SV / FO decision
Handoff / escalation
Release / QPR / long-tail planning
Hsuanchang: effective PS Lv1 DRI from 2025; Aoss: historical PS Lv1 context.
Notes: External is joint interface content; Internal contains Alcedo-only operating details.

## Slide 3
Established P26 co-working model
Four mechanisms operated across one feature-to-closure lifecycle
Feature
PS/SIM sync
Scope / DRI / validation
Issue
Coordinator / DRI / RD
MWI / CR / updates
Technical
Workshops / deep dives
Logs / RCA / DOE
Project
Area/Domain DRI
TW/US relay / release
Requirement / issue
→
Scope + owner
→
Analysis / decision
→
Fix / implementation
→
Validation
→
Release / QPR
Observation: forums existed; handoff from discussion to owner, evidence, validation and closure was not consistently explicit.
Notes: Recap required by preparation deck; this is the operating model, not a meeting list.

## Slide 4
Good points to retain
P26 built useful mechanisms; keep them and close their limits
Practice
What P26 established
Evidence / scale
Feature alignment
Scope, interface, DRI, validation and delivery discussion
2024/9/24 + 2024–25 follow-up
AP-IMS enablement
MIPC/API clarification; fixed / ongoing / reopen
2023/12–2024/11 evolution
Living reference
Relay Metrics definition, support type, status, delivery phase
1,200+ definitions; still evolving
Execution gates
MWI cadence, priority, patch/retest/release
218 total / 111 open snapshot
Validation boundary
Joint, Alcedo and Zion validation distinguished
Feature validation / FLD records
Conditional strength: cadence and references existed; depth, asset readiness and closure varied by topic.
Notes: Strengths are not unconditional success claims.

## Slide 5
P26 collaboration gaps identified
Neutral system-level observations, not team blame
Gap
Observed pattern
Evidence
R&R / routing
Access, coordination, technical ownership and decision authority can converge on one path
Partner-account side effect; Exception governance
Technical coverage
Time-zone relay exists; matching technical peer/RD depth is not always available
US/TW relay; postponed rotation; MWI
Lifecycle ownership
Implementation, validation, release, QPR and retirement span owners
SIM Lock; workaround → P27; QPR
Cross-module convergence
Scenario crosses AP, Modem, SIM, hardware and network
ECC/OOS; AP-IMS; eSIM
Not “there was no support.” The question is whether the path can carry a scenario to technical closure.
Notes: Partner-account firewall was intentional; only internal operating side effect is shown.

## Slide 6
Key events: feature-to-lifecycle control formation
Actual workshops/reviews that changed how PS work was defined
Anchor
What changed
Lesson
2023/12–2024/11 AP-IMS
Interface/API enablement became topic decisions; Q&A fixed/ongoing/reopen
Training must connect to scenario, owner and closure
2024/9/24 PS workshop
Interface docs, message flow, MAL placement, boundary, DRI and delivery
Feature needs execution contract
2024–present Relay Metrics
Living reference; new fields, support type and delivery phase continue
Living feature needs change-control
2024–2025 FLD / Exception
Scope lock, validation classes, technical/commercial boundary
Enablement and verification before commitment
Scale: 4-day PS Deep Dive; ~450 item-level metric follow-up; 1,200+ living catalogue (not additive).
Notes: Multi-topic workshop outcomes remain topic-specific.

## Slide 7
Key events: execution, verification and post-MP long-tail
The gaps became visible at certification, device, release and field-support stages
Event
Concrete evidence
What it exposed
MWI / ECC-OOS
Daily review, patch, retest, SU0/FRC gates; Call Performance less converged
Cadence does not guarantee convergence
eSIM extra-bytes / BWT
P0 partner-visible; 6/8 reproduced across sites
Device/circuit/simulation readiness late
SIM Lock
GID1 read-back → AP retry → SIM/eSIM/IMS impact → patch/QPR
Pre-MP end-to-end failure review needed
QPR / handoff
P26 workaround → successor fix; retirement remains linked
MP is transition, not lifecycle closure
Long-tail = post-MP QPR + workaround retirement + next-program handoff + continuing support.
Notes: Security hot-fix remains an MWI substream.

## Slide 8
Lesson 1 — Feature Verification & Enablement Matrix
Implementation scope and DRI are not enough to define feature done
Feature / scenario
ON/OFF
Ownership
Alcedo UT/RDIT
SV/FO rationale
Zion device IT
Acceptance
Release/QPR
Closure
e.g. carrier
ON/OFF/cond.
Alcedo/Zion/joint
UT/RDIT
Required? reason
Device/AP/SIM/NET
Pass + acceptor
P26/P27/QPR
Evidence + owner
Internal gate
DRI completes matrix; SV/FO reviews SV-not-needed rationale; undefined verification blocks commitment or becomes accepted risk.
Joint gate
Alcedo + Zion confirm carrier/scenario, joint-development boundary, device IT and acceptance owner.
P26 lesson: interface delivered and customer feature validated were different states.
Notes: Editable matrix; directly reflects default state, carrier enablement, joint development and validation boundary.

## Slide 9
Lessons 2–3 — Two readiness gates before commitment
People/decision coverage and test/evidence readiness are separate prerequisites
A — COVERAGE READY
Primary + backup
MUS daytime peer
HQ/domain owner
Convergence owner
Decision + escalation
→
B — EVIDENCE READY
Device / AP / SIM / network
Logs / simulator / circuit
Scenario + pass criteria
Validation owner
Accepted risk if missing
→
COMMITMENT READY
Feature / issue enters
implementation, certification
or release commitment.
P26 evidence:
US-daytime peer gap; postponed rotation; eSIM device/circuit/environment gaps.
Proposed measure: gate completed, or management-accepted risk recorded, before commitment.
Notes: The two gates are related but distinct.

## Slide 10
Internal lessons learned / Alcedo optimization
Preserve governance intent; redesign the operating path
Keep
Change the operating path
Intentional partner-account firewall
Scoped access + coordinator delegation + primary/backup routing
PS Lv1 accountability
PS Lv1 owns completeness; feature/module owners own technical work
MUS US-time triage
Explicit MUS analysis boundary; HQ/RD fix and final ownership
Area/domain mapping
Add decision authority, convergence owner, escalation trigger
Long support horizon
Carry-forward register with QPR, retirement and knowledge transfer
Internal only: detailed access side effects and seven-year planning remain outside External main material.
Notes: Alcedo-internal view; do not frame firewall as a Zion criticism.

## Slide 11
External lessons learned / joint optimization
A shared feature and issue contract at the Alcedo–Zion interface
Before commitment, align
Why it matters
Default ON/OFF + carrier/scenario
Avoid different assumptions about what is active
Alcedo self-contained vs joint development
Avoid implementation/tuning gaps
Alcedo validation vs Zion device IT
Separate interface evidence from system acceptance
Customer-time counterpart + backup
Avoid a contact without decision path
Device/log/test assets + acceptance
Avoid late discovery during P0/certification
QPR / next-program disposition
Keep living items owned after MP
Workshop: shared evidence → joint improvement → Zion feedback / commitment → action items
Notes: Joint, neutral, macro-level content; no private source mechanics.

## Slide 12
P27/P28 proposed operating artifacts
Four proposals with defined problem, gate and adoption measure
Priority
Artifact
Closes
Adoption measure
P1
Feature Verification & Enablement Matrix
Enablement / verification ambiguity
Complete before feature commitment
P2
Coverage & Routing Matrix
Technical-peer / decision gap
Primary + backup before execution peak
P3
Joint Verification Readiness Gate
Late test-asset discovery
Gate complete or risk accepted
P4
Carry-forward / Long-tail Register
QPR / workaround handoff loss
Owner + retirement status
Proposals for P27/P28 — not claims that these artifacts already exist or have been adopted.
Notes: Measures are proposed adoption measures, not P26 achieved results.

## Slide 13
Zion workshop decisions and action register
What should be aligned for P27/P28?
Decision / input
Zion input / choice
Alcedo owner
Zion owner
Target / dependency
Adopt four-artifact model
Accept / modify
PS Lv1 + PM
Zion PS lead
P27/P28 planning
Feature verification boundary
Confirm device IT scope
Feature DRI / SV
Zion feature DRI
Before commitment
Customer-time counterpart
Nominate primary / backup
MUS / HQ
Zion US TL
Before execution peak
Readiness gate
Agree participation
Alcedo PM / DRI
Zion validation
Before high-risk test
Fields to close in workshop: owner, target phase, capacity/dependency, open question.
Retain P26 forums; add explicit feature-to-lifecycle control in P27/P28.
Notes: This is the action/decision close; actual Zion feedback is captured in the workshop.